## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S2 | S2 | US-001 | Discussion on Dask Libraries, Architecture, and Workflow | MUST HAVE | Dask Documentation | Gogula Avinash Kumar | 3- Completed
S2 | S2 | US-001 | Configuration Management and Understanding How Dask Stores and Manages Data Internally | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S3 | S3 | US-001 | Creating Development Environment, Git Repository Setup, and Virtual Environment Configuration | MUST HAVE | github , vs Code | Gogula Avinash Kumar | 3- Completed
S4 | S4 | US-001 | Project Overview: Problem Statement, Outcomes, Modules, and Dask Cluster Setup | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S5 | S5 | US-001 | Topic Finalization and Project Root Folder Structure Setup | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S6 | S6 | US-001 | Client and Cluster Implementation with Log Data Processing Setup | MUST HAVE | google | Gogula Avinash Kumar | 3- Completed
S7 | S7 | US-001 | Dask Distributed Implementation and LocalCluster Workflow Setup | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S8 | S8 | US-001 | Schema Design Discussion and Implementation | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S9 | S9 | US-001 | Log Processing Pipeline Implementation: Parser, Ingestion, Data Cleaning, Loader, and Anomaly Detection | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S10 | S10 | US-001 | Regex Implementation and Milestone 1 Execution | MUST HAVE | Vs Code | Gogula Avinash Kumar | 3- Completed
S11 | S11 | US-001 | Milestone 1: Review, Evaluation, and Viva Presentation | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S12 | S12 | US-001 | tepping into Milestone 2: Workflow Planning and System Expansion | MUST HAVE | No Dependency | Gogula Avinash Kumar | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7